## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | ACTIVITY BARCHART_QUẢN LÝ CỬA HÀNG ĐIỆN THOẠI DI DỘNG
Enter Company Name in cell B2. A legend is in cells I2 through AC2.
| Nhóm 8 | [15 empty] | Complete | [7 empty] | Unfinished
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | [8 empty] | Tháng 9 | [29 empty] | Tháng 10 | [29 empty] | Tháng 11 | [31 empty] | Tháng 12
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Tasks | Loại | Level | Phân công | Tiến trình | Bắt đầu | Thời gian | Column1 | 2001-01-01 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Chọn Đề Tài
| Xác Định Đề Tài | Task | Level_0 | Leader | 100% | 2020-09-13 | 14 | bar: Tháng 9 1900-01-12 to Tháng 9 1900-01-25
| Thống Nhất Cách Làm Việc Nhóm | Task | Level_0 | Leader | 100% | 2020-09-15 | 1 | bar: Tháng 9 1900-01-14
| Thống nhất về ngôn ngữ, công cụ và công nghệ dùng cho đồ án | Task | Level_0 | Leader | 100% | 2020-09-15 | 1 | bar: Tháng 9 1900-01-14
| Phổ biến lộ trình học Front-End, Back-End | Task | Level_0 | Leader | 100% | 2020-09-13 | 2 | bar: Tháng 9 1900-01-14
| Lập kế hoạch(Bảng theo dõi tiến độ) | Task |  | Leader | 100% | 2020-09-15 | 3 | bar: Tháng 9 1900-01-14 to Tháng 9 1900-01-16
Phân Tích Hệ Thống Vấn Đề | bar: Column1
| Phân Tích và Phổ Biến về Quy Mô Phần Mềm | Task | Level_1 |  | 100% | 2020-09-16 | 3 | bar: Tháng 9 1900-01-15 to Tháng 9 1900-01-17
| Xác Định Những Chức Năng Sẽ Có Trong Phần Mềm | Task | Level_1 |  | 100% | 2020-09-17 | 3 | bar: Tháng 9 1900-01-16 to Tháng 9 1900-01-18
| Phân Tích Yêu Cầu Chức Năng và Phi Chức Năng | Task | Level_1 |  | 100% | 2020-09-20 | 7 | bar: Tháng 9 1900-01-19 to Tháng 9 1900-01-25
| Phân Tích và Đặc Tả Mô Hình DFD | Task | Level_1 |  | 100% | 30/9/2020 | 7 | bar: Tháng 9 1900-01-29 to Tháng 10 1900-01-05
| Phân Tích bảng dữ liệu | Task | Level_1 |  | 100% | 2020-10-02 | 5 | bar: Tháng 10 1900-01-01 to Tháng 10 1900-01-05
| Phân Tích UseCase | Task |  |  | 100% | 2020-10-05 | 8 | bar: Tháng 10 1900-01-04 to Tháng 10 1900-01-11
Thiết Kế Hệ Thống | bar: Column1
| Danh sách Biểu mẫu, Quy định | Task |  |  | 100% | 2020-10-12 | 7 | bar: Tháng 10 1900-01-11 to Tháng 10 1900-01-18
| Bảng yêu cầu- bảng trách nhiệm cho từng chức năng | Task |  |  | 100% | 2020-10-12 | 7 | bar: Tháng 10 1900-01-11 to Tháng 10 1900-01-18
| Thiết Kế DFD mức 0 | Task |  |  | 100% | 2020-10-20 | 7 | bar: Tháng 10 1900-01-19 to Tháng 10 1900-01-25
| Thiết kế DFD mức 1 | Task |  |  | 100% | 2020-10-20 | 7 | bar: Tháng 10 1900-01-19 to Tháng 10 1900-01-25
| Thiết kế DFD tổng quát từng chức năng | Task |  |  | 100% | 2020-10-20 | 7 | bar: Tháng 10 1900-01-19 to Tháng 10 1900-01-25
| Thiết kế Sequence Diagram | Task |  |  | 100% | 2020-11-07 | 7 | bar: Tháng 11 1900-02-06 to Tháng 11 1900-02-10
| Thiết kế Activity Diagram | Task |  |  | 100% | 2020-11-12 | 3 | bar: Tháng 11 1900-02-11 to Tháng 11 1900-02-15
| Thiết Kế UseCase Diagram | Task | Level_1 |  | 100% | 2020-10-27 | 7 | bar: Tháng 10 1900-01-26 to Tháng 11 1900-02-01
| Đặc Tả UseCase Diagram | Task | Level_1 |  | 100% | 2020-11-03 | 3 | bar: Tháng 11 1900-02-02 to Tháng 11 1900-02-04
| Thiết Kế ERD | Task | Level_1 |  | 100% | 2020-10-27 | 7 | bar: Tháng 10 1900-01-26 to Tháng 11 1900-02-01
Thiết kế phần mềm
| Thiết kế giao diện phần mềm | Task |  |  | 100% | 2020-11-07 | 7 | bar: Tháng 11 1900-02-06 to Tháng 11 1900-02-12
| Thiết kế xử lý | Task |  |  | 100% | 2020-11-07 | 7 | bar: Tháng 11 1900-02-06 to Tháng 11 1900-02-12
| Thiết kế dữ liệu | Task |  |  | 100% | 2020-11-07 | 7 | bar: Tháng 11 1900-02-06 to Tháng 11 1900-02-12
Xây Dựng Phần Mềm
| Quy Định về Quy Tắc Commit Trên Github | Task | Level_1 |  | 100% | 15/9/2020 | 1 | bar: Tháng 9 1900-01-14
| Phân Tích Các Dữ Liệu | Task | Level_1 |  | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Xây Dựng CSDL | Feature |  |  | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Xây Dựng Lớp DTO từng chức năng | Feature | Level_1 |  | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Xây Dựng Lớp DAO tứng chức năng | Feature | Level_1 |  | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Xây Dựng Lớp BUS từng chức năng | Feature | Level_1 |  | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Xây Dựng Lớp GUI tứng chức năng | Feature | Level_1 |  | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Thu nhập hình ảnh, icon cho giao diện | Feature |  |  | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Xây Dựng Giao Diện | Feature | Level_1 |  | 100% | 2020-11-15 | 14 | bar: Column1; Tháng 11 1900-02-14 to Tháng 11 1900-02-27
Tổng hợp | bar: Column1
| Tổng hợp phần code | Task |  |  | 100% | 2020-11-29 | 6 | bar: Tháng 11 1900-02-28 to Tháng 12 1900-02-02
| Tổng hợp Diagram | Task |  |  | 100% | 2020-11-29 | 6 | bar: Tháng 11 1900-02-28 to Tháng 12 1900-02-02
| Tổng hợp các phân tích thiết kế | Task |  |  | 100% | 2020-11-29 | 6 | bar: Tháng 11 1900-02-28 to Tháng 12 1900-02-02
Các Chức Năng được Xây Dựng trên hệ thống
Chia Các Branch Dev Trên Github | Đăng nhập | Task |  | Trung | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Xuất danh sách(tài khoản, khách hàng, phiếu nhập, thống kê) | Task |  | Trường | 100% | 2020-01-15 | 14
| Phân quyền | Task |  | Vi | 100% | 2020-01-15 | 14
Phân Tích Các Chuẩn Dữ Liệu Của API | Quản lý nhân viên | Task |  | Tuấn | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Quản lý tài khoản | Task |  | Tuyền | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Quản lý tài khoản | Task |  | Viễn | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Quản lý sản phẩm | Task |  | Trường | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Quản lý loại sản phẩm | Task |  | Tuyền | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Quản lý nhập hàng | Task |  | Trân | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Thống kê | Task |  | Trân | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Quản lý hóa đơn | Task |  | Vũ | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Quản lý nhà cung cấp | Task |  | Tuấn | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Quản lý chương trình khuyến mãi | Task |  | Vi | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Bán hàng | Task |  | Viễn | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| In hóa đơn bán hàng | Task |  | Vũ | 100% | 2020-11-15 | 14 | bar: Tháng 11 1900-02-14 to Tháng 11 1900-02-27
| Xuất phiếu nhập hàng | Task |  | Trung | 100% | 2020-11-15 | 14 | bar: Column1; Tháng 11 1900-02-14 to Tháng 11 1900-02-27
Kiểm thử phần mềm
| Kiểm thử giao diện | Task |  |  | 100% | 2020-11-29 | 2 | bar: Tháng 11 1900-02-28 to Tháng 11 1900-01-29
| Kiểm thử các chức năng | Task |  |  | 100% | 2020-11-29 | 2 | bar: Tháng 11 1900-02-28 to Tháng 11 1900-01-29
| Kiểm thử hiệu năng hệ thống | Task | Level_1 |  | 100% | 2020-11-29 | 2 | bar: Column1; Tháng 11 1900-02-28 to Tháng 11 1900-01-29
Đánh giá phần mềm
| Đánh giá phần mềm | Task |  |  | 100% | 2020-11-30 | 1 | bar: Column1; Tháng 11 1900-01-29
Báo cáo đồ án
| Lập báo cáo đồ án | Task |  |  | 100% | 2020-02-12 | 2 | bar: Tháng 12 1900-02-02 to Tháng 12 1900-02-03
| Báo cáo đồ án | Task |  |  |  | 2020-05-12